## Sheet1
Sl. No. | Group No. | Project Name | Name | Allocated Module | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6
1 | 4 | Cab Booking App | Akash | Trip Selection | Requirement Specification and Analysis | Design of module and entire structure | Spring boot with REST app and testing | UI design and developement | App integration | Deployment
2 | 4 | Cab Booking App | Aman | Trip commute | Requirement Specification and Analysis | Design of module and entire structure | Spring boot with REST app and testing | UI design and developement | App integration | Deployment
3 | 4 | Cab Booking App | Anchita | Feedback+payments | Requirement Specification and Analysis | Design of module and entire structure | Spring boot with REST app and testing | UI design and developement | App integration | Deployment
4 | 4 | Cab Booking App | Shubham | Cab allocation(driver side) | Requirement Specification and Analysis | Design of module and entire structure | Spring boot with REST app and testing | UI design and developement | App integration | Deployment
5 | 4 | Cab Booking App | Surjani | Login+Signup | Requirement Specification and Analysis | Design of module and entire structure | Spring boot with REST app and testing | UI design and developement | App integration | Deployment
6 | 4 | Cab Booking App | Vineeta | Admin | Requirement Specification and Analysis | Design of module and entire structure | Spring boot with REST app and testing | UI design and developement | App integration | Deployment
7 | 4 | Cab Booking App | Vishal | Cab allocation(customer side) | Requirement Specification and Analysis | Design of module and entire structure | Spring boot with REST app and testing | UI design and developement | App integration | Deployment