## Readme
Guidelines for usage of the Query Tracking Sheet
1 | Enter all requirements related queries raised throught project duration in this sheet to keep all queries at one place.
2 | Insert queries raised and answered in proposal phase as well into this sheet, when the project begins. This will ensure all replies and assumptions made in proposal phase are knows to the development team.
3 | Projects sent/received updated query tracking sheet to/from Customer. Only the latest version of the sheet should be maintained at designated place (to avoid confusion/rework).
4 | Projects should request Customer /Customer Collaborator(CC) to enter their queries and replies also in this sheet. Even if customer does not enter, Projects should keep this sheet updated for important queries, if queries are received by mails or documents.
5 | The status of all pending queries should be taken in the project meetings. PL should escalate to Customer Collaborator/Customer for open queries.

## Query Sheet
PROJECT GROUP IV : CAB BOOKING APPLICATION
Query Tracking Sheet
Sr # | Type | Module | Query Text | Reply Text | Raised By (Name) | Open (Date) | Reply By (Name) | Closed (Date) | Phase Raised In | Phase Closed in | CR (Y/N) | Status | Query TAT (Turn Around Time) in days
1 |  | 5 | To what extent we have to restrict our application - should it include both the driver side and customer side functionalities? If yes, then what all could be the extent of their rights? | Let new customers to register/login (for existing customers) and proceed with cab bookings for a source and destination of their choice. Also, let new drivers to register by providing necessary documents and existing drivers to log into the sysytem and proceed with their daily rides as and when they're assigned one. | Akash Verma (46001179) | 2019-11-01 | Vishal Soni (46001972) | 2019-11-02 | Requirement Phase | Requirement Phase |  | Closed
2 |  | 5 | Login Screen: Allows the valid user(customer/ driver/admin) to log into to the system and display the appropriate option screens according to the role of the user. What does the above statement imply? Should the contents on the web page be available to all (for viewing) or should it be restricted to registered users? | The home page could have an about us column (with the application's contact information, etc.) which could be available to all but other than that the user must be logged in, either as a customer/ driver/ admin to access their specific functionalities. | Aman Dungarwal (46001780) | 2019-11-01 | Vineeta (46004887) | 2019-11-02 | Requirement Phase | Requirement Phase |  | Closed
3 |  | 5 | What exactly should be the contents of the home page??Should it include only sign in and registration links or it can it also include advertisements for upcoming offers? | Let's keep it to login and signup links for now, can extend later based on progress. | Anchita Roy (46002265) | 2019-11-01 | Surjani Biswas (46001701) | 2019-11-02 | Requirement Phase | Requirement Phase |  | Closed
4 |  | 5 | How can the resources(images,icons,logos etc) be made available to us? | Not a valid question now, will discuss later. | Shubham (46002223) | 2019-11-01 | Shubham (46002223) |  | Design Phase |  |  | On-hold
5 |  | 5 | Should we include the cancellation feature available to both driver and customer? If yes, then should it be based on pre-defined set time interval within which only cancellation option would be available? | Let's keep it aside for discussion later. | Surjani Biswas (46001701) | 2019-11-01 | Anchita Roy (46002265) |  | Requirement Phase |  |  | On-hold
7 |  | 5 | Any predefined color scheme for the website? | No set pre-defined schemes but maybe follow a an overall black theme for all the navigation tabs and green for buttons. | Vineeta (46004887) | 2019-11-02 | Aman Dungarwal (46001780) | 2019-11-02 | Development Phase | Development Phase |  | Closed
8 |  | 5 | Any hover action needs to be done on the menu bar? | Can be included if required | Vishal Soni (46001972) | 2019-11-02 | Akash Verma (46001179) | 2019-11-02 | Design Phase | Design Phase |  | Closed
|  | 5 | Should the menu bar be displayed on all the pages including registration pages? | No | Akash Verma (46001179) | 2019-11-02 | Vishal Soni (46001972) | 2019-11-02 | Development Phase | Development Phase
10 |  | 5 | How long the user must be in session? | You can have a session timeout based on your application. | Aman Dungarwal (46001780) | 2019-11-02 | Vineeta (46004887) | 2019-11-02 | Development Phase | Development Phase |  | Closed
11 |  | 5 | How would the final trip fare be calculated? Should it be based on distance or would it be dynamically generated? | Make it dynamically generated based on both distance covered and the overall time taken for trip completion. | Anchita Roy (46002265) | 2019-11-02 | Surjani Biswas (46001701) | 2019-11-02 | Design Phase | Design Phase |  | Closed
12 |  | 5 | After registering where should the user go?Login or Homepage? | Login Page. | Shubham (46002223) | 2019-11-02 | Surjani Biswas (46001701) | 2019-11-03 | Requirement Phase | Design Phase |  | Closed
13 |  | 5 | Where should the procedure end? After completing the ride or after showing the payment page? | On success page after feedback submittion. | Surjani Biswas (46001701) | 2019-11-02 | Anchita Roy (46002265) | 2019-11-03 | Development Phase | Development Phase |  | Closed
14 |  | 5 | Should all attributes of the bean be declared as String? | As per the requirements. | Vineeta (46004887) | 2019-11-03 | Aman Dungarwal (46001780) | 2019-11-04 | Design Phase | Design Phase |  | Closed
15 |  | 5 | Should we use only one controller or multiple controllers? | One front controller to handle all the rest of the micro-services. | Vishal Soni (46001972) | 2019-11-03 | Akash Verma (46001179) | 2019-11-04 | Development Phase | Development Phase |  | Closed
Note on B5: ====== ID#AAAAD7XQgoo Sonal Desai (2019-11-10 15:12:16) QC = Q by Client QP = Q by Patni
Note on L5: ====== ID#AAAAD7XQgok patni (2019-11-10 15:12:16) Has this query resulted in a CR (record shd be present in the CR tracking Sheet)
Note on M5: ====== ID#AAAAD7XQgog dabrelee (2019-11-10 15:12:16) Open Active Closed On-hold
Note on N5: ====== ID#AAAAD7XQgos Meenu S (2019-11-10 15:12:16) TAT is the difference in days between the time query is raised to the time query is closed. Average TAT can be included be in the weekly status report to the client