## User stories
| Main User Story | Sub-Task
1 | Login / Signup | Add Customer
Add Driver
Find Customer
Find Driver
2 | Trip Selector | Save Trip Details
Get Locations
Estimate Price
3 | Cab Allocation (Customer) | Get Near-by Vehicles
Book a Cab
List Past Trips
4 | Cab Allocation (Driver) | List drivers
List all trips
Search for Booking
Get Booking Details
Get Driver by Email
5 | Transit | Start Trip
End Trip
Rate Trip
Update Driver Rating
Update Vehicle Status
Final Fare Generation
Get Booking Details
6 | Payments and Feedback | Add Payment Transactions
Update Feedback Report
Update Customer Wallet Balance
Get Customer Details
Get Booking Details
7 | Admin | Get Booking Details
Delete Driver
Update Driver
Find Driver
Get all Reports
Get all Drivers

## Surjani
Task No. | Task Name | Estimated hours/Time | Actual Time Taken | Allotted on day | Comments
1 | Login / Signup
1.1 | Add Customer
1.1.1 | Html Page | 3 | 3 | Saturday
1.1.2 | Component | 1 | 1 | Saturday
1.1.3 | Validations + Exception Handling | 1.5 | 1.5 | Friday
1.2 | Add Driver
1.2.1 | Html Page | 1 | 1 | Saturday
1.2.2 | Component | 1 | 1 | Saturday
1.2.3 | Validations + Exception Handling | 1.5 | 1.5 | Friday
1.3 | Find Customer
1.3.1 | Html Page | 2 | 2 | Monday
1.3.2 | Component | 1.5 | 1.5 | Monday
1.3.3 | Validations + Exception Handling | 1.5 | 1.5 | Friday
1.4 | Find Driver
1.4.1 | Html Page | 1 | 1 | Monday
1.4.2 | Component | 1 | 1 | Monday
1.4.3 | Validations + Exception Handling | 1.5 | 1.5 | Friday

## Akash
Task No. | Task Name | Estimated hours/Time | Actual Time Taken | Allotted on day | Comments
1 | Trip Selector
1.1 | Save Trip Details
1.1.1 | Html Page | 2 | 2 | Saturday
1.1.2 | Component | 1 | 1 | Saturday
1.1.3 | Validations + Exception Handling | 2 | 2 | Friday
1.2 | Get Locations
1.2.1 | Html Page | 1 | 1 | Monday
1.2.2 | Component | 1 | 1 | Monday
1.2.3 | Validations + Exception Handling | 0.5 | 0.5 | Thursday
1.3 | Estimate Price
1.3.1 | Html Page | 1 | 1 | Monday
1.3.2 | Component | 1 | 1 | Monday
1.3.3 | Validations + Exception Handling | 3 | 3 | Saturday

## Vishal
Task No. | Task Name | Estimated hours/Time | Actual Time Taken | Allotted on day | Comments
1 | Cab Allocation (Customer)
1.1 | Get nearby vehicles
1.1.1 | HTML Page | 3 | 3 | Monday
1.1.2 | Component | 1 | 1 | Saturday
1.1.3 | Validations + Exception Handling | 2 | 2 | Friday
1.2 | Book a cab
1.2.1 | HTML Page | 3 | 3 | Monday
1.2.2 | Component | 1.5 | 1.5 | Tuesday
1.2.3 | Validations + Exception Handling | 1.5 | 1.5 | Friday
1.3 | List all past trips
1.3.1 | HTML Page | 2 | 2 | Tuesday
1.3.2 | Component | 1.5 | 1.5 | Tuesday
1.3.3 | Validations + Exception Handling | 2 | 2 | Saturday

## Shubham
Task No. | Task Name | Estimated hours/Time | Actual Time Taken | Allotted on day | Comments
1 | Cab Allocation (Driver)
1.1 | Get list of all vehicles
1.1.1 | Html Page | 3 | 3 | Saturday
1.1.2 | Component | 1 | 1 | Saturday
1.1.3 | Validations + Exception Handling | 1.5 | 1.5 | Monday
1.2 | Get list of all past trips
1.2.1 | Html Page | 1 | 1 | Saturday
1.2.2 | Component | 1 | 1 | Tuesday
1.2.3 | Validations + Exception Handling | 1.5 | 1.5 | Wednesday
1.3 | Get a driver by email
1.3.1 | Html Page | 2 | 2 | Monday
1.3.2 | Component | 1.5 | 1.5 | Monday
1.3.3 | Validations + Exception Handling | 1.5 | 1.5 | Friday
1.4 | Search for bookings
1.4.1 | Html Page | 1 | 1 | Monday
1.4.2 | Component | 1 | 1 | Tuesday
1.4.3 | Validations + Exception Handling | 1.5 | 1.5 | Friday
1.5 | Get booking details
1.5.1 | Html Page | 1 | 1 | Tuesday
1.5.2 | Component | 1 | 1 | Tuesday
1.5.3 | Validations + Exception Handling | 1.5 | 1.5 | Saturday

## Aman
Task No. | Task Name | Estimated hours/Time | Actual Time Taken | Allotted on day | Comments
1 | Transit
1.1 | Start Trip
1.1.1 | Html Page | 3 | 3 | Saturday
1.1.2 | Component | 1 | 1 | Saturday
1.1.3 | Validations + Exception Handling | 1.5 | 1.5 | Friday
1.2 | End Trip
1.2.1 | Html Page | 1 | 1 | Saturday
1.2.2 | Component | 1 | 1 | Tuesday
1.2.3 | Validations + Exception Handling | 1.5 | 1.5 | Friday
1.3 | Rate trip
1.3.1 | Html Page | 2 | 2 | Monday
1.3.2 | Component | 1.5 | 1.5 | Wednesday
1.3.3 | Validations + Exception Handling | 1.5 | 1.5 | Friday
1.4 | Update Driver Rating
1.4.1 | Html Page | 1 | 1 | Monday
1.4.2 | Component | 1 | 1 | Monday
1.4.3 | Validations + Exception Handling | 1.5 | 1.5 | Thursday
1.5 | End Trip
1.5.1 | Html Page | 1 | 1 | Saturday
1.5.5 | Component | 1 | 1 | Monday
1.5.3 | Validations + Exception Handling | 1.5 | 1.5 | Friday
1.6 | Rate trip
1.6.1 | Html Page | 2 | 2 | Monday
1.6.2 | Component | 1.5 | 1.5 | Monday
1.6.3 | Validations + Exception Handling | 1.5 | 1.5 | Saturday
1.7 | Update Driver Rating
1.7.1 | Html Page | 1 | 1 | Monday
1.7.2 | Component | 1 | 1 | Monday
1.7.3 | Validations + Exception Handling | 1.5 | 1.5 | Saturday

## Anchita
Task No. | Task Name | Estimated hours/Time | Actual Time Taken | Allotted on day | Comments
1 | Payments and Feedback
1.1 | Add payment transactions
1.1.1 | Html Page | 3 | 3 | Saturday
1.1.2 | Component | 1 | 1 | Monday
1.1.3 | Validations + Exception Handling | 1.5 | 1.5 | Friday
1.2 | Update feedback reports
1.2.1 | Html Page | 1 | 1 | Saturday
1.2.2 | Component | 1 | 1 | Saturday
1.2.3 | Validations + Exception Handling | 1.5 | 1.5 | Tuesday
1.3 | Update customer wallet balance
1.3.1 | Html Page | 2 | 2 | Wednesday
1.3.2 | Component | 1.5 | 1.5 | Wednesday
1.3.3 | Validations + Exception Handling | 1.5 | 1.5 | Friday
1.4 | Get customer details
1.4.1 | Html Page | 1 | 1 | Monday
1.4.2 | Component | 1 | 1 | Monday
1.4.3 | Validations + Exception Handling | 1.5 | 1.5 | Friday
1.5 | Get booking details
1.5.1 | Html Page | 1 | 1 | Saturday
1.5.5 | Component | 1 | 1 | Monday
1.5.3 | Validations + Exception Handling | 1.5 | 1.5 | Friday

## Vineeta
Task No. | Task Name | Estimated hours/Time | Actual Time Taken | Allotted on day | Comments
1 | Admin
1.1 | Get all booking details
1.1.1 | Html Page | 3 | 3 | Saturday
1.1.2 | Component | 1 | 1 | Saturday
1.1.3 | Validations + Exception Handling | 1.5 | 1.5 | Friday
1.2 | Delete Driver
1.2.1 | Html Page | 1 | 1 | Saturday
1.2.2 | Component | 1 | 1 | Tuesday
1.2.3 | Validations + Exception Handling | 1.5 | 1.5 | Friday
1.3 | Update Driver
1.3.1 | Html Page | 2 | 2 | Monday
1.3.2 | Component | 1.5 | 1.5 | Wednesday
1.3.3 | Validations + Exception Handling | 1.5 | 1.5 | Friday
1.4 | Find Driver
1.4.1 | Html Page | 1 | 1 | Monday
1.4.2 | Component | 1 | 1 | Monday
1.4.3 | Validations + Exception Handling | 1.5 | 1.5 | Thursday
1.5 | Get all reports
1.5.1 | Html Page | 1 | 1 | Saturday
1.5.5 | Component | 1 | 1 | Monday
1.5.3 | Validations + Exception Handling | 1.5 | 1.5 | Friday
1.6 | Get all drivers
1.6.1 | Html Page | 2 | 2 | Monday
1.6.2 | Component | 1.5 | 1.5 | Monday
1.6.3 | Validations + Exception Handling | 1.5 | 1.5 | Saturday